## WBS
Task Group | Task | Assign | From | To | % completed | Note
Project Management | Họp dự án mỗi ngày | ALL | 8:00PM | 10:00PM |  | Thông qua Facebook/Team View
CM Management | Cài đặt .Net Core | ALL |  |  |  | .NET Core 3.1
CM Management | Cài đặt TeamView | ALL |  |  |  | TeamView 14
CM Management | SQL | ALL |  |  |  | SQL 2012
Training | C# | ALL |  |  |  | https://www.w3schools.com/cs/
Training | MVC Framework | ALL |  |  |  | https://www.w3schools.com/asp/default.ASP
Training | Angular | ALL |  |  |  | https://www.w3schools.com/angular/
Project Implementation | Khảo sát yêu cầu chức năng | ALL
| Vẽ usecase model | Nhựt
Phân tích thiết kế
| Accout | Nhựt |  |  |  | vẽ sequence diagram
| Login/Logout | Phát |  |  |  | vẽ sequence diagram
| Thiết kế CSDL | Phát |  |  |  | vẽ data diagram
| Thiết kế giao diện | ALL
| Lập trình | ALL
| Kiểm thử | ALL

## Risk Mgmt
No | Risk | Risk Description | Risk Type | Risk Group | Affects | Probability | Exponent | Strategy Type | Strategy Description
1 | Rớt môn | Không hoàn thành yêu cầu môn học | People |  | 5 | 50% | 2.5 | Avoid Risk | Học hành chăm chỉ, làm bài tập đầy đủ
2 | [6 empty] | 0 | Minimize Affects | Xem lại bài giảng
3 | [6 empty] | 0 | Plan B | Học lại
4 | Chưa học MVC | Chưa thành thạo MVC và chưa áp dụng vào đề tài nào | Technology |  | 3 | 25% | 0.75 | Avoid Risk | Bắt đầu tham gia các khóa học
5 | [6 empty] | 0 | Minimize Affects | Thực hành thử demo để có thể làm đồ án thực tế
6 | [6 empty] | 0 | Plan B | Copy 1 số code trên mạng
7 | Trễ deadline | Chưa hoàn thành kịp tiến độ | People |  | 3 | 25% | 0.75 | Avoid Risk | Kiểm soát thời gian và công việc
8 | [6 empty] | 0 | Minimize Affects | Tăng năng suất khi trễ
9 | [6 empty] | 0 | Plan B | Nhờ thêm bạn làm phụ
10 | chưa học angular | Chưa tiếp cận được với Angular | Technology |  | 4 | 50% | 2 | Avoid Risk | Bắt đầu tham gia các khóa học
11 | [6 empty] | 0 | Minimize Affects | 1 bạn trong nhóm học trước và chỉ lại cho thành viên khác
12 | [6 empty] | 0 | Plan B | Nhờ giúp đỡ từ những người đã tiếp cận Angular
13 | Trễ deadline | có thành viên bị ốm hay có công việc cần giải quyết không thể làm theo đúng tiến độ | People |  | 2 | 25% | 0.5 | Avoid Risk | Thể dục thể thao tăng cường đề kháng.
14 | [6 empty] | 0 | Minimize Affects | Người còn lại làm việc nhiều hơn.
15 | [6 empty] | 0 | Plan B | Chép code

## Ref
Risk group | Mức độ rủi ro | Xác suất rủi ro | Task Group | Risk type | Strategy Type | Member
C1 - Customers & Users | 1 | 10% | Project Management | Technology | Avoid Risk | Nhựt
C2 - Scope & requirement | 2 | 25% | CM Management | People | Minimize Affects | Phát
C3 - Execution | 3 | 50% | Training | Organizational | Plan B | ALL
C4 - Environment | 4 | 75% | Project Implementation | Tool
| 5 | 100% | Package and Release | Requirement
Estimation